## Sheet1
Due | Activity | Description | Status | 2019-09-21 | 2019-09-22 | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 2019-09-30 | 2019-10-01 | 2019-10-02
2019-09-23 | Research | find datasets and APIs to use in the Proj verify if datasets have the outputs we require | in progress
2019-09-25 | Data Wrangling | transform and merge datasets | Not started | [5 empty] | if needed
2019-09-28 | Charts & Maps | Create and plot all proposed charts and maps | Not started
2019-09-30 | Final review & conclusions | review the code and confirm all questions are answered. | Not started
2019-10-02 | PPT | Prepare the PPT and test the 10min presentatation before class | Not started
WBS | Activity | Description / Owner |  | 2019-09-21 | 2019-09-22 | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 2019-09-30 | 2019-10-01 | 2019-10-02
1.1 | Research | Get a Real Estate dataset by zip code and with data up to y 2000 (at least) | in progress | bar: 2019-09-21 to 2019-09-23
1.2 | Research | Get a Real Estate dataset by zip code and with data up to y 2000 (at least) | in progress | bar: 2019-09-21 to 2019-09-23
1.3 | Research | Get a Real Estate dataset by zip code and with data up to y 2000 (at least) | in progress | bar: 2019-09-21 to 2019-09-23
1.4 | Research | Get a Inflation rates and Federal Reserve Interest rates datasets with data up to y 2000 (at least) | in progress | bar: 2019-09-21 to 2019-09-23
2.1 | Data Wrangling | Transform/format your dataset | Not started | bar: 2019-09-24 to 2019-09-26
2.2 | Data Wrangling | Transform/format your dataset | Not started | bar: 2019-09-24 to 2019-09-26
2.3 | Data Wrangling | Transform/format your dataset | Not started | bar: 2019-09-24 to 2019-09-26
2.4 | Data Wrangling | Transform/format your dataset | Not started | bar: 2019-09-24 to 2019-09-26
3.1 | Charts & Maps | Plot (2x) : (bar chart) top 10 zip codes with greatest and lowest market price variation over inflation | Not started | bar: 2019-09-26 to 2019-09-28
3.2 | Charts & Maps | Plot (1x) : (line chart) real estate market price vs inflation rate vs fed interest rates (OR PAIRED T-TEST - Hipotesis test) | Not started | bar: 2019-09-26 to 2019-09-28
3.3 | Charts & Maps | Plot (2x) : (line chart) market price variation (country) 10 to 12 years before and after subprime crisis. | Not started | bar: 2019-09-26 to 2019-09-28
3.4 | Charts & Maps | Google maps plot for the top 10 (or 5) zip codes with greatest and lowest market variation | Not started | bar: 2019-09-26 to 2019-09-28
4.1 | Final review & conclusions | review the code and confirm all questions are answered. Start preparing PPT | Not started | bar: 2019-09-29 to 2019-09-30
4.2 | Final review & conclusions | review the code and confirm all questions are answered. Start preparing PPT | Not started | bar: 2019-09-29 to 2019-09-30
4.2 | Final review & conclusions | review the code and confirm all questions are answered. Start preparing PPT | Not started | bar: 2019-09-29 to 2019-09-30
4.2 | Final review & conclusions | review the code and confirm all questions are answered. Start preparing PPT | Not started | bar: 2019-09-29 to 2019-09-30
2019-10-02 | PPT | Prepare the PPT and test the 10min presentatation before class | Not started | 2019-10-01: ALL